## ACMP Process
Master Change Management Process Checklist
Derived from information in the ACMP® Standard for Change Management© - First Edition
Prepared by jTask, Inc. San Mateo, CA
sales@jtask.com
Published - 20240101 (ISO Date)
This process checklist is built based on ACMP Standard for Change Management, it should be adapted to fit your specific situation.
ACMP Standard for Change Management
l Does not mandate any activities or process steps.
l Is not a one-size fits all approach and can be scaled to fit.
l The level of detail of the Change Management Plan should reflect the complexity and risk of the change effort.
Checklist | Completed | Evidence / File Name | Comment
| Started/WIP/NA/Yes | Location
5.1 Evaluate Change Impact and Organizational Readiness
5.1.1 Define the Change
5.1.2 Determine Why the Change is Required
5.1.3 Develop a Clear Vision of the Future State
5.1.4 Identify Goals, Objectives and Success Criteria
5.1.5 Identify Sponsors Accountable for the Change
5.1.6 Identify Stakeholders Affected by the Change
5.1.7 Assess the Change Impact
5.1.8 Assess Alignment of the Change with Organizational Strategic Objectives and Performance Measurement
5.1.9 Assess External Factors that may Affect Organizational Change
5.1.10 Assess Organization Culture(s) Related to the Change
5.1.11 Assess Organizational Capacity for Change
5.1.12 Assess Organizational Readiness for Change
5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages
5.1.14 Assess Learning Capabilities
5.1.15 Conduct Change Risks Assessment
5.2 Formulate the Change Management Strategy
5.2.1 Develop the Communication Strategy
5.2.2 Develop the Sponsorship Strategy
5.2.3 Develop the Stakeholder Engagement Strategy
5.2.4 Develop the Change Impact and Readiness Strategy
5.2.5 Develop the Learning and Development Strategy
5.2.6 Develop the Measurement and Benefit Realization Strategy
5.2.7 Develop the Sustainability Strategy
5.3 Develop the Change Management Plan
5.3.1 Develop a Comprehensive Change Management Plan
5.3.2 Integrate Change Management and Project Management Plans
5.3.3 Review and Approve the Change Management Plan in Collaboration with Project Leadership
5.3.4 Develop Feedback Mechanisms to Monitor Performance to Plan
5.4 Execute the Change Management Plan
5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan
5.4.2 Modify the Change Management Plan as Required
5.5 Complete the Change Management Effort
5.5.1 Evaluate the Outcome Against the Objectives
5.5.2 Design and Conduct Lessons Learned Evaluation and Provide Results to Establish Internal Best Practices
5.5.3 Gain Approval for Completion Transfer of Ownership and Release of Resources
Acknowledgement:​
jTask acknowledges the Association for Change Management Professionals® (ACMP®) Standard for Change Management©, hereinafter referred to as “the ACMP Standard”, as being the basis for developing this template.
Some material that has been directly quoted from the ACMP Standard content is clearly designated indicating what paragraph in the ACMP Standard contains the quoted material.​
​
Legal Information:​
jTask™, the jTask logo, jTask Consulting™, jTask CCMP Training™, and jTask CCMP Webapp are trademarks of jTask, Inc. ​
The ACMP logo, ACMP® and the Association of Change Management Professionals® are registered trademarks. Certified Change Management Professional™ (CCMP™) is a trademark of ACMP. The Standard for Change Management© is a copyright of the ACMP. ​
MemoryPak™ is a trademark of Watson Educational Games.​
All other trademarks, registered trademarks, service marks, and related branding marks (possibly unmarked) used in this course are the legal property of their respective owner

## ACMP Process Inputs and Outputs
Change Management Process Steps Inputs and Outputs
Template is derived from information in the ACMP® Standard for Change Management© - First Edition
Prepared by jTask, Inc. San Mateo, CA
sales@jtask.com
Published - 20240101 (ISO Date)
This is a complete list of ACMP Standard for Change Management, processes and inputs and outputs.
# | Process Group | Process Step | Process Sub-step | Input | Output | Study Comments | jTask Study Comment
1 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.1 Define the Change | NA | Business Case | Change Definition
2 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.1 Define the Change | NA | Research | Charter |  | Research as an Input stands out because it could apply to every Input.
3 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.1 Define the Change | NA | Charter
4 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.1 Define the Change | NA | Strategic Plan
5 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.1 Define the Change | NA | Success Measures
6 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.2 Determine Why the Change is Required | NA | Business Case | Business Case
7 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.2 Determine Why the Change is Required | NA | Change Definition | Charter
8 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.2 Determine Why the Change is Required | NA | Charter
9 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.2 Determine Why the Change is Required | NA | Strategic Plan
10 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.2 Determine Why the Change is Required | NA | Success Measures
11 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.3 Develop a Clear Vision of the Future State | NA | Organization Vision, Mission, Values | Vision Statement
12 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.3 Develop a Clear Vision of the Future State | NA | Business Case
13 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.3 Develop a Clear Vision of the Future State | NA | Change Definition
14 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.3 Develop a Clear Vision of the Future State | NA | Strategic Plan
15 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.4 Identify Goals, Objectives and Success Criteria | NA | Business Case | Change Objectives and Goals
16 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.4 Identify Goals, Objectives and Success Criteria | NA | Charter | Success Criteria and Measures
17 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.4 Identify Goals, Objectives and Success Criteria | NA | Strategic Plan
18 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.4 Identify Goals, Objectives and Success Criteria | NA | Vision Statement
19 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.4 Identify Goals, Objectives and Success Criteria | NA | Change Definition
20 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.5 Identify Sponsors Accountable for the Change | NA | Change Definition | Sponsor Identification
21 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.5 Identify Sponsors Accountable for the Change | NA | Charter | Sponsor Assessment
22 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.5 Identify Sponsors Accountable for the Change | NA | Stakeholder Analysis |  |  | Stakeholder Analysis as an Input stands out because 5.1.6 has not happen.
23 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.5 Identify Sponsors Accountable for the Change | NA | Current Organizational Charts and Profiles
24 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.6 Identify Stakeholders Affected by the Change | NA | Change Definition | Stakeholder Analysis
25 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.6 Identify Stakeholders Affected by the Change | NA | Vision Statement
26 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.6 Identify Stakeholders Affected by the Change | NA | Current Organizational Charts and Profiles
27 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.6 Identify Stakeholders Affected by the Change | NA | Research |  |  | Research as an Input stands out because it could apply to every Input.
28 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.6 Identify Stakeholders Affected by the Change | NA | Charter
29 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.7 Assess the Change Impact | NA | Change Definition | Change Impact Assessment
30 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.7 Assess the Change Impact | NA | Vision Statement
31 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.7 Assess the Change Impact | NA | Research |  |  | Research as an Input stands out because it could apply to every Input.
32 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.7 Assess the Change Impact | NA | Stakeholder Analysis
33 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.8 Assess Alignment of the Change with Organizational Strategic Objectives and Performance Measurement | NA | Strategic Plan | Organizational Alignment Assessment
34 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.8 Assess Alignment of the Change with Organizational Strategic Objectives and Performance Measurement | NA | Current Vision Statement | Modifications to Organizational and Enterprise Performance Targets (Goals and Objectives)
35 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.8 Assess Alignment of the Change with Organizational Strategic Objectives and Performance Measurement | NA | Future State Vision Statement | Modifications to Strategic Plan
36 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.8 Assess Alignment of the Change with Organizational Strategic Objectives and Performance Measurement | NA | Case for Change | Modification of Business Case
37 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.8 Assess Alignment of the Change with Organizational Strategic Objectives and Performance Measurement | NA | Risk Plan | Modification of Vision Statement
38 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.9 Assess External Factors that may Affect Organizational Change | NA | Business Case | External Environment Impact Assessment
39 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.9 Assess External Factors that may Affect Organizational Change | NA | Vision Statement
40 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.9 Assess External Factors that may Affect Organizational Change | NA | Strategic Plan
41 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.10 Assess Organization Culture(s) Related to the Change | NA | Core Values and Behaviors | Culture Assessment
42 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.10 Assess Organization Culture(s) Related to the Change | NA | Current Communication Channels, Tools, and Methods
43 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.10 Assess Organization Culture(s) Related to the Change | NA | Opinion Surveys and Feedback Assessments |  |  | Opinion Surveys and Feedback Assessments as an Input stands out because it could apply to multiple inputs.
44 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.10 Assess Organization Culture(s) Related to the Change | NA | Vision Statement
45 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.11 Assess Organizational Capacity for Change | NA | Competency Assessment | Organizational Change Capacity Assessment
46 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.11 Assess Organizational Capacity for Change | NA | Culture Assessment
47 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.11 Assess Organizational Capacity for Change | NA | Organization’s Historical Experience with Change
48 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.11 Assess Organizational Capacity for Change | NA | Stakeholder Assessment |  |  | It was called Stakeholder Analysis in 5.1.6 Output.
49 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.11 Assess Organizational Capacity for Change | NA | External Environment Impact Assessment
50 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.11 Assess Organizational Capacity for Change | NA | Change Impact Assessment
51 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.11 Assess Organizational Capacity for Change | NA | Inventory of Change-Related Resources
52 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.12 Assess Organizational Readiness for Change | NA | Change Objectives and Goals | Organizational Change Readiness Assessment
53 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.12 Assess Organizational Readiness for Change | NA | Culture Assessment
54 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.12 Assess Organizational Readiness for Change | NA | Organizational Change Capacity Assessment
55 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.12 Assess Organizational Readiness for Change | NA | Organizational Alignment Assessment
56 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.12 Assess Organizational Readiness for Change | NA | Sponsorship Alignment Assessment
57 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.12 Assess Organizational Readiness for Change | NA | Vision Statement
58 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.12 Assess Organizational Readiness for Change | NA | Risk Assessment
59 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages | NA | Change Objectives and Goals | Communication Needs Assessment
60 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages | NA | Culture Assessment
61 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages | NA | Organizational Change Capacity Assessment
62 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages | NA | Sponsorship Alignment Assessment |  |  | It was called Sponsor Assessment in 5.1.5 Output
63 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages | NA | Stakeholder Analysis
64 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages | NA | Current Communication Channels, Tools, and Methods
65 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages | NA | Vision Statement
66 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages | NA | Risk Assessment
67 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.14 Assess Learning Capabilities | NA | Stakeholder Analysis | Learning Needs Assessment
68 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.14 Assess Learning Capabilities | NA | Change Impact Assessment
69 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.14 Assess Learning Capabilities | NA | Communication Needs Assessment
70 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.14 Assess Learning Capabilities | NA | Culture Assessment
71 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.14 Assess Learning Capabilities | NA | Organizational Change Capacity Assessment
72 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.14 Assess Learning Capabilities | NA | Organizational Alignment Assessment
73 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.15 Conduct Change Risks Assessment | NA | Stakeholder Analysis | Change Risks Assessment
74 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.15 Conduct Change Risks Assessment | NA | Change Impact Assessment | Risk Register
75 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.15 Conduct Change Risks Assessment | NA | Culture Assessment
76 | 5.1 Evaluate Change Impact and Organizational Readiness | 5.1.15 Conduct Change Risks Assessment | NA | Organizational Change Capacity Assessment
77 | 5.2 Formulate the Change Management Strategy | 5.2.1 Develop the Communication Strategy | NA | Change Definition | Communication Strategy
78 | 5.2 Formulate the Change Management Strategy | 5.2.1 Develop the Communication Strategy | NA | Change Impact Assessment
79 | 5.2 Formulate the Change Management Strategy | 5.2.1 Develop the Communication Strategy | NA | Current Communication Channels, Tools, and Methods
80 | 5.2 Formulate the Change Management Strategy | 5.2.1 Develop the Communication Strategy | NA | Organizational Change Readiness Assessment
81 | 5.2 Formulate the Change Management Strategy | 5.2.1 Develop the Communication Strategy | NA | Project Charter and Project Documentation
82 | 5.2 Formulate the Change Management Strategy | 5.2.1 Develop the Communication Strategy | NA | Stakeholder Analysis
83 | 5.2 Formulate the Change Management Strategy | 5.2.1 Develop the Communication Strategy | NA | Vision Statement
84 | 5.2 Formulate the Change Management Strategy | 5.2.2 Develop the Sponsorship Strategy | NA | Change Risks | Sponsorship Strategy
85 | 5.2 Formulate the Change Management Strategy | 5.2.2 Develop the Sponsorship Strategy | NA | Organizational Change Readiness Assessment
86 | 5.2 Formulate the Change Management Strategy | 5.2.2 Develop the Sponsorship Strategy | NA | Sponsorship Alignment Assessment |  |  | It was called Sponsor Assessment in 5.1.5 Output.
87 | 5.2 Formulate the Change Management Strategy | 5.2.2 Develop the Sponsorship Strategy | NA | Stakeholder Analysis
88 | 5.2 Formulate the Change Management Strategy | 5.2.3 Develop the Stakeholder Engagement Strategy | NA | Current State Analysis | Stakeholder Engagement Strategy
89 | 5.2 Formulate the Change Management Strategy | 5.2.3 Develop the Stakeholder Engagement Strategy | NA | Change Impact Assessment
90 | 5.2 Formulate the Change Management Strategy | 5.2.3 Develop the Stakeholder Engagement Strategy | NA | Current Communication Channels, Tools, and Methods
91 | 5.2 Formulate the Change Management Strategy | 5.2.3 Develop the Stakeholder Engagement Strategy | NA | Communication Strategy
92 | 5.2 Formulate the Change Management Strategy | 5.2.3 Develop the Stakeholder Engagement Strategy | NA | Sponsorship Strategy
93 | 5.2 Formulate the Change Management Strategy | 5.2.3 Develop the Stakeholder Engagement Strategy | NA | Stakeholder Analysis
94 | 5.2 Formulate the Change Management Strategy | 5.2.4 Develop the Change Impact and Readiness Strategy | NA | Stakeholder Engagement Strategy | Change Impact and Readiness Strategy
95 | 5.2 Formulate the Change Management Strategy | 5.2.4 Develop the Change Impact and Readiness Strategy | NA | Change Impact Assessment
96 | 5.2 Formulate the Change Management Strategy | 5.2.5 Develop the Learning and Development Strategy | NA | Learning Needs Assessment | Learning and Development Strategy
97 | 5.2 Formulate the Change Management Strategy | 5.2.5 Develop the Learning and Development Strategy | NA | Stakeholder Analysis
98 | 5.2 Formulate the Change Management Strategy | 5.2.6 Develop the Measurement and Benefit Realization Strategy | NA | Strategic Plan | Measurement and Benefit Realization Strategy
99 | 5.2 Formulate the Change Management Strategy | 5.2.6 Develop the Measurement and Benefit Realization Strategy | NA | Case for Change | Revised Performance and Rewards Targets
100 | 5.2 Formulate the Change Management Strategy | 5.2.6 Develop the Measurement and Benefit Realization Strategy | NA | Change Objectives and Goals
101 | 5.2 Formulate the Change Management Strategy | 5.2.6 Develop the Measurement and Benefit Realization Strategy | NA | Project Charter
102 | 5.2 Formulate the Change Management Strategy | 5.2.6 Develop the Measurement and Benefit Realization Strategy | NA | Success Criteria |  |  | It was called Success Criteria and Measures in 5.1.4.
103 | 5.2 Formulate the Change Management Strategy | 5.2.7 Develop the Sustainability Strategy | NA | Business Case | Sustainability Strategy
104 | 5.2 Formulate the Change Management Strategy | 5.2.7 Develop the Sustainability Strategy | NA | Change Objectives and Goals
105 | 5.2 Formulate the Change Management Strategy | 5.2.7 Develop the Sustainability Strategy | NA | Change Risk Assessment
106 | 5.2 Formulate the Change Management Strategy | 5.2.7 Develop the Sustainability Strategy | NA | Project Charter and Documentation
107 | 5.2 Formulate the Change Management Strategy | 5.2.7 Develop the Sustainability Strategy | NA | Strategic Plan
108 | 5.2 Formulate the Change Management Strategy | 5.2.7 Develop the Sustainability Strategy | NA | Success Criteria and Measures
109 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.1 Resource Plan | Change Management Resources, Roles, and Responsibilities Strategy | Resource Plan |  | "Change Management Resources, Roles, and Responsibilities Strategy" does not exist as a "Strategy" in the ACMP Standard.
110 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.1 Resource Plan | Communication Strategy
111 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.1 Resource Plan | Learning and Development Strategy
112 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.1 Resource Plan | Change Resources Inventory
113 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.1 Resource Plan | Procurement Guidelines and Policies |  |  | Procurement Guidelines and Policies stands out because it only appears in the Resource Plan.
114 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.2 Sponsorship Plan | Sponsorship Strategy | Sponsorship Plan
115 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.2 Sponsorship Plan | Sponsorship Alignment Assessment |  |  | It was called Sponsor Assessment in 5.1.5.
116 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.2 Sponsorship Plan | Stakeholder Analysis
117 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.2 Sponsorship Plan | Sponsor Assessment |  |  | Is this a repeat of Sponsorship Alignment Assessment?
118 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.3 Stakeholder Engagement Plan | Stakeholder Analysis | Stakeholder Engagement Plan
119 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.3 Stakeholder Engagement Plan | Stakeholder Engagement Strategy
120 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.3 Stakeholder Engagement Plan | Communication Strategy
121 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.3 Stakeholder Engagement Plan | Sponsorship Strategy
122 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.3 Stakeholder Engagement Plan | Change Risks
123 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Communication Strategy | Communication Plan
124 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Current Communication Channels, Tools, and Methods
125 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Key Messages |  |  | Key messages as an Input stands out because it is generic.
126 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Learning and Development Strategy
127 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Project Charter and Documentation
128 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Project Schedule and Plan
129 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Sponsorship Strategy
130 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Stakeholder Analysis
131 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Stakeholder Engagement Strategy
132 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.4 Communication Plan | Transition Strategy |  |  | Transition Strategy does not exist as a "Strategy" in the ACMP Standard.
133 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.5 Learning and Development Plan | Learning and Development Strategy | Learning and Development Plan
134 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.5 Learning and Development Plan | Stakeholder Analysis
135 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.5 Learning and Development Plan | Learning Needs Assessment
136 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.6 Measurement and Benefit Realization Plan | Measurement and Benefit Realization Strategy | Measurement and Benefit Realization Plan
137 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.6 Measurement and Benefit Realization Plan | Change Definition
138 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.6 Measurement and Benefit Realization Plan | Change Objectives and Goals
139 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.6 Measurement and Benefit Realization Plan | Vision Statement
140 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.7 Sustainability Plan | Status Report/Benefits Gap Analysis | Sustainability Plan
141 | 5.3 Develop the Change Management Plan | 5.3.1 Develop a Comprehensive Change Management Plan | 5.3.1.7 Sustainability Plan | Resource Plan
142 | 5.3 Develop the Change Management Plan | 5.3.2 Integrate Change Management and Project Management Plans | NA | Change Management Plan | Change Management Plan (updated)
143 | 5.3 Develop the Change Management Plan | 5.3.2 Integrate Change Management and Project Management Plans | NA | Project Charter and Project Documentation | Project Plan (updated)
144 | 5.3 Develop the Change Management Plan | 5.3.2 Integrate Change Management and Project Management Plans | NA | Project Schedule and Plan
145 | 5.3 Develop the Change Management Plan | 5.3.3 Review and Approve the Change Management Plan in Collaboration with Project Leadership | NA | Change Management Plan | Change Management Plan (approved)
146 | 5.3 Develop the Change Management Plan | 5.3.3 Review and Approve the Change Management Plan in Collaboration with Project Leadership | NA | Project Plan
147 | 5.3 Develop the Change Management Plan | 5.3.4 Develop Feedback Mechanisms to Monitor Performance to Plan | NA | Communication Plan | Communication Plan (updated)
148 | 5.3 Develop the Change Management Plan | 5.3.4 Develop Feedback Mechanisms to Monitor Performance to Plan | NA | Learning and Development Plan | Learning and Development Plan (updated)
149 | 5.3 Develop the Change Management Plan | 5.3.4 Develop Feedback Mechanisms to Monitor Performance to Plan | NA | Measurement and Benefit Realization Plan | Measurement and Benefit Realization Plan (updated)
150 | 5.3 Develop the Change Management Plan | 5.3.4 Develop Feedback Mechanisms to Monitor Performance to Plan | NA | Project Schedule and Plan | Stakeholder Engagement Plan (updated)
151 | 5.3 Develop the Change Management Plan | 5.3.4 Develop Feedback Mechanisms to Monitor Performance to Plan | NA | Stakeholder Engagement Plan
152 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.1 Execute Resource Plan | Change Management Plan | Change Management Plan
153 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.1 Execute Resource Plan | Project Schedule and Plan | Financial Resources Update/Impact Reports
154 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.1 Execute Resource Plan | Resource Plan | Human Resources Update/Impact Reports
155 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.1 Execute Resource Plan |  | Information Resources Update/Impact Reports
156 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.1 Execute Resource Plan |  | Physical Resources Update/Impact
157 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.1 Execute Resource Plan |  | Reports |  | "Reports" as an Output stands out because it is generic.
158 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.2 Execute Communication Plan | Project Plan | Communication Delivery
159 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.2 Execute Communication Plan | Communication Plan
160 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.2 Execute Communication Plan | Stakeholder Engagement Plan
161 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.3 Execute Sponsorship Plan | Sponsorship Plan | Sponsor Activities
162 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.3 Execute Sponsorship Plan | Communication Plan | Sponsor Competency Building Activities
163 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.3 Execute Sponsorship Plan | Stakeholder Engagement Plan
164 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.4 Execute Stakeholder Engagement Plan | Stakeholder Engagement Plan | Stakeholder Engagement Activities
165 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.4 Execute Stakeholder Engagement Plan | Sponsorship Plan | Sponsor Engagement Activities
166 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.4 Execute Stakeholder Engagement Plan | Communication Plan | Resistance Management Activities
167 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.5 Execute Learning and Development Plan | Learning and Development Plan | Learning and Performance Evaluation Reports
168 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.5 Execute Learning and Development Plan | Change Resources, Roles, and Responsibilities Plan
169 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.5 Execute Learning and Development Plan | Supporting Learning and Development
170 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.5 Execute Learning and Development Plan | Materials (e.g., job aids)
171 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.6 Execute Measurement and Benefit Realization | Change Management Plan | Measurement and Benefit Realization Reports
172 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.6 Execute Measurement and Benefit Realization | Measurement and Benefit Realization Plan | Benefits Realization Activities
173 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.7 Execute Sustainability Plan | Sustainability Plan | Communication Events
174 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.7 Execute Sustainability Plan | Measurement Baselines | Benefits Reviews
175 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.7 Execute Sustainability Plan |  | Business Performance Reports
176 | 5.4 Execute the Change Management Plan | 5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan | 5.4.1.7 Execute Sustainability Plan |  | Evaluations and Reviews
177 | 5.4 Execute the Change Management Plan | 5.4.2 Modify the Change Management Plan as Required | NA | Change Management Plan | Change Management Plan (updated)
178 | 5.4 Execute the Change Management Plan | 5.4.2 Modify the Change Management Plan as Required | NA | Project Schedule and Plan
179 | 5.5 Complete the Change Management Effort | 5.5.1 Evaluate the Outcome Against the Objectives | NA | Change Objectives and Goals | Change Objectives Analysis Outcomes and Next Steps
180 | 5.5 Complete the Change Management Effort | 5.5.1 Evaluate the Outcome Against the Objectives | NA | Measurement and Benefit Realization Plan
181 | 5.5 Complete the Change Management Effort | 5.5.1 Evaluate the Outcome Against the Objectives | NA | Sustainability Plan
182 | 5.5 Complete the Change Management Effort | 5.5.2 Design and Conduct Lessons Learned Evaluation and Provide Results to Establish Internal Best Practices | NA | Case for Change | Lessons Learned Evaluation
183 | 5.5 Complete the Change Management Effort | 5.5.2 Design and Conduct Lessons Learned Evaluation and Provide Results to Establish Internal Best Practices | NA | Success Criteria and Measures | Remediation Plan |  | Remediation Plan is created as part of Lessons Learned.
184 | 5.5 Complete the Change Management Effort | 5.5.2 Design and Conduct Lessons Learned Evaluation and Provide Results to Establish Internal Best Practices | NA | Change Management Plan
185 | 5.5 Complete the Change Management Effort | 5.5.3 Gain Approval for Completion Transfer of Ownership and Release of Resources | NA | Change Objectives and Goals | Final Summary Report
186 | 5.5 Complete the Change Management Effort | 5.5.3 Gain Approval for Completion Transfer of Ownership and Release of Resources | NA | Measurement and Benefit Realization Plan | Change Initiative Completion
187 | 5.5 Complete the Change Management Effort | 5.5.3 Gain Approval for Completion Transfer of Ownership and Release of Resources | NA | Lessons Learned Report
188 | 5.5 Complete the Change Management Effort | 5.5.3 Gain Approval for Completion Transfer of Ownership and Release of Resources | NA | Future Strategy Plan |  |  | Strategy Plan as an Input stands out because it is generic.
189 | 5.5 Complete the Change Management Effort | 5.5.3 Gain Approval for Completion Transfer of Ownership and Release of Resources | NA | Agreement on Ownership Transfer
190 | 5.5 Complete the Change Management Effort | 5.5.3 Gain Approval for Completion Transfer of Ownership and Release of Resources | NA | Resource Release Approval
Acknowledgement:​
jTask acknowledges the Association for Change Management Professionals® (ACMP®) Standard for Change Management©, hereinafter referred to as “the ACMP Standard”, as being the basis for developing this template.
Some material that has been directly quoted from the ACMP Standard content is clearly designated indicating what paragraph in the ACMP Standard contains the quoted material.​
​
Legal Information:​
jTask™, the jTask logo, jTask Consulting™, jTask CCMP Training™, and jTask CCMP Webapp are trademarks of jTask, Inc. ​
The ACMP logo, ACMP® and the Association of Change Management Professionals® are registered trademarks. Certified Change Management Professional™ (CCMP™) is a trademark of ACMP. The Standard for Change Management© is a copyright of the ACMP. ​
MemoryPak™ is a trademark of Watson Educational Games.​
All other trademarks, registered trademarks, service marks, and related branding marks (possibly unmarked) used in this course are the legal property of their respective owner

## ACMP Based Change Plan
Master Change Management Plan
Derived from information in the ACMP® Standard for Change Management© - First Edition
Prepared by jTask, Inc. San Mateo, CA
sales@jtask.com
Published - 20240101 (ISO Date)
This process checklist is built based on ACMP Standard for Change Management, it should be adapted to fit your specific situation.
ACMP Standard for Change Management
l Does not mandate any activities or process steps.
l Is not a one-size fits all approach and can be scaled to fit.
l The level of detail of the Change Management Plan should reflect the complexity and risk of the change effort.
§5.4 - Execute
Work Breakdown Structure (WBS) | Start Date | End Date | Resource | Complete | Outputs | ACMP Process Steps | Comments
§5.1 - Analysis | Add Dates | Add Dates | Add Resource | Started/WIP/NA/Yes
Evaluate Change Impact and Organizational Readiness (Set-up Meeting Schedule) | [5 empty] | 5.1 Evaluate Change Impact and Organizational Readiness
Meet with Project Sponsor | 2024-07-01 | 2024-07-15 | Sam Doe | WIP | Notes or full report covering | 5.1.1 Define the Change
Meet with Project Management Office (PMO) | 2024-07-01 | 2024-07-15 | Sam Doe | WIP | all the items listed in the | 5.1.2 Determine Why the Change is Required
Meet with Sponsors (AKA Business Leaders / Success Owners) - 1 | 2024-07-01 | 2024-07-15 | Sam Doe | WIP | ACMP Standard. | 5.1.3 Develop a Clear Vision of the Future State
Meet with Sponsors (AKA Business Leaders / Success Owners) - 2 | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.4 Identify Goals, Objectives and Success Criteria
Meet with Sponsors (AKA Business Leaders / Success Owners) - N… | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.5 Identify Sponsors Accountable for the Change
Meet with Key Stakeholders (top quadrant of power interest chart) | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.6 Identify Stakeholders Affected by the Change
Meet with Key Stakeholder Groups (top quadrant of power interest chart) | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.7 Assess the Change Impact
Additional Meetings (?) | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.8 Assess Alignment of the Change with Organizational Strategic Objectives and Performance Measurement
Meet with Human Resources | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.9 Assess External Factors that may Affect Organizational Change
Meet with Corporate Communications | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.10 Assess Organization Culture(s) Related to the Change
Meet with Learning and Development (Training) | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.11 Assess Organizational Capacity for Change
Conduct Surveys (?) | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.12 Assess Organizational Readiness for Change
Send out surveys to key stakeholders (Customer dependent) | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.13 Assess Communication Needs, Communication Channels and Ability to Deliver Key Messages
Analyze stakeholder survey results | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.14 Assess Learning Capabilities
Wrap-up Analysis and Report(?) | 2024-07-01 | 2024-07-15 | Sam Doe | WIP |  | 5.1.15 Conduct Change Risks Assessment
Optional - Write XYZ Change Impact and Organizational Readiness Report | 2024-07-01 | 2024-07-15 | Sam Doe | WIP
Review report with Project Sponsor and PMO
Schedule Executive Change Management Strategy review session(s) | Amount of time allocated for Analysis is dependent on |  |  |  | A report is usually prepared
| * Complexity of the Project |  |  |  | when the customer is
| * Size of the Project |  |  |  | willing to invest in
| * Perceived risk of Stakeholder Adoption by an Organization |  |  |  | an analysis.
§5.4 - Execute
Work Breakdown Structure (WBS) | Start Date | End Date | Resource | Complete | Outputs | ACMP Process Steps | Comments
§5.2 - Strategy | Add Dates | Add Dates | Add Resource | Started/WIP/NA/Yes
Formulate the Change Management Strategy | [5 empty] | 5.2 Formulate the Change Management Strategy
Before finalizing the plan, convene a meeting to assess the CM Strategy and secure endorsement from the leadership team. | [5 empty] | 5.2.1 Develop the Communication Strategy
Present the Change Management (CM) strategic choices for approval (cost and resourcing) | 2024-07-15 | 2024-07-31 | Sam Doe | WIP |  | 5.2.2 Develop the Sponsorship Strategy
Before finalizing the plan, convene multiple meetings to assess the CM Strategy and secure endorsement from the leadership team. | [5 empty] | 5.2.3 Develop the Stakeholder Engagement Strategy
Present the Communication strategic choices for approval (cost and resourcing) | 2024-07-15 | 2024-07-31 | Sam Doe | WIP |  | 5.2.4 Develop the Change Impact and Readiness Strategy
Present the Learning and Development (Training) strategic choices for approval (cost and resourcing) | 2024-07-15 | 2024-07-31 | Sam Doe | WIP |  | 5.2.5 Develop the Learning and Development Strategy
Present the Sponsorship strategic choices for approval (cost and resourcing) | 2024-07-15 | 2024-07-31 | Sam Doe | WIP |  | 5.2.6 Develop the Measurement and Benefit Realization Strategy
Present the Stakeholder Engagement strategic choices for approval (cost and resourcing) | 2024-07-15 | 2024-07-31 | Sam Doe | WIP |  | 5.2.7 Develop the Sustainability Strategy
Present the Change Impact and Readiness strategic choices for approval (cost and resourcing) | 2024-07-15 | 2024-07-31 | Sam Doe | WIP
Present the Measurement and Benefit Realization strategic choices for approval (cost and resourcing) | 2024-07-15 | 2024-07-31 | Sam Doe | WIP
Present the Sustainability strategic choices for approval (cost and resourcing) | 2024-07-15 | 2024-07-31 | Sam Doe | WIP
§5.4 - Execute
Work Breakdown Structure (WBS) | Start Date | End Date | Resource | Complete | Outputs | ACMP Process Steps | Comments
§5.3 - Plan | Add Dates | Add Dates | Add Resource | Started/WIP/NA/Yes
Develop the Change Management Plan | [5 empty] | 5.3 Develop the Change Management Plan
Before finalizing the plan, convene a meeting to assess the CM Strategy and secure endorsement from the leadership team. | [5 empty] | 5.3.1 Develop a Comprehensive Change Management Plan
Create Change Management Plan | 2024-07-31 | 2024-11-30 | Sam Doe | WIP |  | 5.3.2 Integrate Change Management and Project Management Plans
Build detailed plan based on strategic choices | 2024-07-31 | 2024-11-30 | Sam Doe | WIP |  | 5.3.3 Review and Approve the Change Management Plan in Collaboration with Project Leadership
Communication Choice 1 ( Example Branding) | 2024-07-31 | 2024-11-30 | Sam Doe | WIP |  | 5.3.4 Develop Feedback Mechanisms to Monitor Performance to Plan
Change Commitment Stage - Awareness | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Activity 1 | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Activity 2 | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Activity …... | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Communication Choice 2 (Example Milestone Emails) | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Activity 1 | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Activity 2 | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Activity …... | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Stakeholder Engagement Choice 1 (Town Hall) | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Activity …. | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Etc…
Integrate Change Management and Project Management Plans | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Review and Approve the Change Management Plan in Collaboration with Project Leadership | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
Develop Feedback Mechanisms to Monitor Performance to Plan | 2024-07-31 | 2024-11-30 | Sam Doe | WIP
§5.4 - Execute
Work Breakdown Structure (WBS) | Start Date | End Date | Resource | Complete | Outputs | ACMP Process Steps | Comments
§5.5 - Complete | Add Dates | Add Dates | Add Resource | Started/WIP/NA/Yes
Complete the Change Management Effort | [5 empty] | 5.5 Complete the Change Management Effort
Evaluate the Outcome Against the Objectives | 2024-12-01 | 2024-12-31 | Sam Doe | WIP |  | 5.5.1 Evaluate the Outcome Against the Objectives
Design and Conduct Lessons Learned Evaluation and Provide Results to Establish Internal Best Practices | 2024-12-01 | 2024-12-31 | Sam Doe | WIP |  | 5.5.2 Design and Conduct Lessons Learned Evaluation and Provide Results to Establish Internal Best Practices
Gain Approval for Completion Transfer of Ownership and Release of Resources | 2024-12-01 | 2024-12-31 | Sam Doe | WIP |  | 5.5.3 Gain Approval for Completion Transfer of Ownership and Release of Resources
5.4 Execute the Change Management Plan
5.4.1 Execute, Manage, and Monitor Implementation of the Change Management Plan
5.4.2 Modify the Change Management Plan as Required
Acknowledgement:​
jTask acknowledges the Association for Change Management Professionals® (ACMP®) Standard for Change Management©, hereinafter referred to as “the ACMP Standard”, as being the basis for developing this template.
Some material that has been directly quoted from the ACMP Standard content is clearly designated indicating what paragraph in the ACMP Standard contains the quoted material.​
​
Legal Information:​
jTask™, the jTask logo, jTask Consulting™, jTask CCMP Training™, and jTask CCMP Webapp are trademarks of jTask, Inc. ​
The ACMP logo, ACMP® and the Association of Change Management Professionals® are registered trademarks. Certified Change Management Professional™ (CCMP™) is a trademark of ACMP. The Standard for Change Management© is a copyright of the ACMP. ​
MemoryPak™ is a trademark of Watson Educational Games.​
All other trademarks, registered trademarks, service marks, and related branding marks (possibly unmarked) used in this course are the legal property of their respective owner

## ACMP Deliverables
Change Management Process Deliverables
Derived from information in the ACMP® Standard for Change Management© - First Edition
Prepared by jTask, Inc. San Mateo, CA
sales@jtask.com
Published - 20240101 (ISO Date)
This process checklist is built based on ACMP Standard for Change Management, it should be adapted to fit your specific situation.
Checklist ID | Type | Checklist | Status | Owner | Due Date | Background Information
1 | Process | Evaluate Change Impact and Organizational Readiness | Not started | TBD
2 | Deliverable/Output | Change Definition | Not started | TBD
3 | Deliverable/Output | Charter | Not started | TBD
4 | Deliverable/Output | Business Case | Not started | TBD
5 | Deliverable/Output | Vision Statement | Not started | TBD
6 | Deliverable/Output | Change Objectives and Goals | Not started | TBD
7 | Deliverable/Output | Success Criteria and Measures | Not started | TBD
8 | Deliverable/Output | Sponsor Identification | Not started | TBD
9 | Deliverable/Output | Sponsor Assessment | Not started | TBD
10 | Deliverable/Output | Stakeholder Analysis | Not started | TBD
11 | Deliverable/Output | Change Impact Assessment | Not started | TBD
12 | Deliverable/Output | Organization Alignment Assessment | Not started | TBD
13 | Deliverable/Output | Modification to Organizational Enterprise Performance Targets (Goals and Objectives) | Not started | TBD
14 | Deliverable/Output | Modification to Strategic Plan | Not started | TBD
15 | Deliverable/Output | Modification of Business Case | Not started | TBD
16 | Deliverable/Output | Modification of Vision Statement | Not started | TBD
17 | Deliverable/Output | External Environment Impact Assessment | Not started | TBD
18 | Deliverable/Output | Culture Assessment | Not started | TBD
19 | Deliverable/Output | Organizational Change Capacity Assessment | Not started | TBD
20 | Deliverable/Output | Organizational Readiness Change Assessment | Not started | TBD
21 | Deliverable/Output | Communication Needs Assessment | Not started | TBD
22 | Deliverable/Output | Learning Needs Assessment | Not started | TBD
23 | Deliverable/Output | Change Risk Assessment | Not started | TBD
24 | Deliverable/Output | Risk Register | Not started | TBD
25 | Process | Formulate the Change Management Strategy | Not started | TBD
26 | Deliverable/Output | Communication Strategy | Not started | TBD
27 | Deliverable/Output | Sponsorship Strategy | Not started | TBD
28 | Deliverable/Output | Stakeholder Engagement Strategy | Not started | TBD
29 | Deliverable/Output | Change Impact and Readiness Strategy | Not started | TBD
30 | Deliverable/Output | Learning and Development Strategy | Not started | TBD
31 | Deliverable/Output | Measurement and Benefit Realization Strategy | Not started | TBD
32 | Deliverable/Output | Sustainability Strategy | Not started | TBD
33 | Process | Develop the Change Management Plan | Not started | TBD
34 | Deliverable/Output | Change Management Plan | Not started | TBD
35 | Deliverable/Output | Resource Plan | Not started | TBD
36 | Deliverable/Output | Communication Plan | Not started | TBD
37 | Deliverable/Output | Impact Assessment and Readiness Plan | Not started | TBD
38 | Deliverable/Output | Sponsorship Plan | Not started | TBD
39 | Deliverable/Output | Stakeholder Engagement Plan | Not started | TBD
40 | Deliverable/Output | Learning and Development Plan | Not started | TBD
41 | Deliverable/Output | Measurement and Benefit Realization Plan | Not started | TBD
42 | Deliverable/Output | Sustainability Plan | Not started | TBD
43 | Deliverable/Output | Change Management and Project Management Plans Integrated | Not started | TBD
44 | Deliverable/Output | Change Plan Approved by Project Leadership | Not started | TBD
45 | Deliverable/Output | Feedback Mechanisms to Monitor Performance Plan Set-up | Not started | TBD
46 | Process | Execute the Change Management Plan | Not started | TBD
47 | Deliverable/Output | Resource Plan Updated | Not started | TBD
48 | Deliverable/Output | Communication Delivery Reports | Not started | TBD
49 | Deliverable/Output | Sponsor Activities Reports | Not started | TBD
50 | Deliverable/Output | Sponsor Competency Building Activity Reports | Not started | TBD
51 | Deliverable/Output | Stakeholder Engagement Activity Reports | Not started | TBD
52 | Deliverable/Output | Sponsor Engagement Activity Reports | Not started | TBD
53 | Deliverable/Output | Resistance Management Activity Reports | Not started | TBD
54 | Deliverable/Output | Learning and Performance Evaluation Reports | Not started | TBD
55 | Deliverable/Output | Measurement and Benefits Realization Reports | Not started | TBD
56 | Deliverable/Output | Benefits Realization Activity Reports | Not started | TBD
57 | Deliverable/Output | Sustainability Communication Event Reports | Not started | TBD
58 | Deliverable/Output | Sustainability Benefits Reviews | Not started | TBD
59 | Deliverable/Output | Sustainability Business Performance Reports | Not started | TBD
60 | Deliverable/Output | Sustainability Evaluations and Reviews | Not started | TBD
61 | Process | Complete the Change Management Effort | Not started | TBD
62 | Deliverable/Output | Change Objectives Analysis Outcomes and Next Steps Report | Not started | TBD
63 | Deliverable/Output | Lessons Learned Evaluation | Not started | TBD
64 | Deliverable/Output | Remediation Plan | Not started | TBD
65 | Deliverable/Output | Final Summary Report | Not started | TBD
66 | Deliverable/Output | Change Initiative Completion Approval Sign-off | Not started | TBD
Acknowledgement:​
jTask acknowledges the Association for Change Management Professionals® (ACMP®) Standard for Change Management©, hereinafter referred to as “the ACMP Standard”, as being the basis for developing this template.
Some material that has been directly quoted from the ACMP Standard content is clearly designated indicating what paragraph in the ACMP Standard contains the quoted material.​
​
Legal Information:​
jTask™, the jTask logo, jTask Consulting™, jTask CCMP Training™, and jTask CCMP Webapp are trademarks of jTask, Inc. ​
The ACMP logo, ACMP® and the Association of Change Management Professionals® are registered trademarks. Certified Change Management Professional™ (CCMP™) is a trademark of ACMP. The Standard for Change Management© is a copyright of the ACMP. ​
MemoryPak™ is a trademark of Watson Educational Games.​
All other trademarks, registered trademarks, service marks, and related branding marks (possibly unmarked) used in this course are the legal property of their respective owner